## Project Plan Sample
Status Key
Completed
In-Progress
On-Going
Behind
Not Started
Hold
Project Name: | Sample Project |  |  |  |  | Removed
Milestone | Category | Sub-Category | Task / Activity | Owner | Target End Date | Status | Notes
Milestone A |  |  | Task #A1 |  | 2018-01-08 | Completed
Milestone A |  |  | Task #A2 |  | 2018-01-11 | In-Progress
Milestone A |  |  | Task #A3 |  | 2018-01-16 | Behind
Milestone A |  |  | Task #A4 |  | 2018-01-19 | Not Started
Milestone A |  |  | Task #A5 |  | 2018-01-23 | Not Started
Milestone B |  |  | Task #B1 |  | 2018-01-12 | Completed
Milestone B |  |  | Task #B2 |  | 2018-01-19 | Completed
Milestone B |  |  | Task #B3 |  | 2018-01-19 | In-Progress
Milestone B |  |  | Task #B4 |  | 2018-01-26 | On-Going
Milestone C |  |  | Task #C1 |  | 2018-01-19 | Completed
Milestone C |  |  | Task #C2 |  | 2018-01-23 | Hold
Milestone C |  |  | Task #C3 |  | 2018-01-26 | In-Progress
Milestone C |  |  | Task #C4 |  | 2018-01-29 | Behind
Milestone C |  |  | Task #C5 |  | 2018-01-25 | On-Going
Milestone D |  |  | Task #D1 |  | 2018-01-24 | Not Started
Milestone D |  |  | Task #D2 |  | 2018-01-30 | Behind
Milestone D |  |  | Task #D3 |  | 2018-01-30 | Hold
Milestone D |  |  | Task #D4 |  | 2018-01-31 | Not Started

## Gantt Chart Sample
* = an automatically calculated cell
MILESTONE | TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Milestone A
| Task #A1 | 2018-01-05 | 5 | 2018-01-08 | 4 | 4 | 0 |  | 100%
| Task #A2 | 2018-01-08 | 8 | 2018-01-11 | 4 | 3.2 | 0.8 |  | 80%
| Task #A3 | 2018-01-11 | 11 | 2018-01-16 | 6 | 3.6 | 2.4 |  | 60%
| Task #A4 | 2018-01-14 | 14 | 2018-01-19 | 6 | 2.4 | 3.6 |  | 40%
| Task #A5 | 2018-01-17 | 17 | 2018-01-23 | 7 | 1.4 | 5.6 |  | 20%
Milestone B
| Task #B1 | 2018-01-09 | 9 | 2018-01-12 | 4 | 4 | 0 |  | 100%
| Task #B2 | 2018-01-12 | 12 | 2018-01-19 | 8 | 6.4 | 1.6 |  | 80%
| Task #B3 | 2018-01-17 | 17 | 2018-01-19 | 3 | 1.8 | 1.2 |  | 60%
| Task #B4 | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 |  | 40%
Milestone C
| Task #C1 | 2018-01-15 | 15 | 2018-01-19 | 5 | 5 | 0 |  | 100%
| Task #C2 | 2018-01-22 | 22 | 2018-01-23 | 2 | 1.6 | 0.4 |  | 80%
| Task #C3 | 2018-01-22 | 22 | 2018-01-26 | 5 | 3 | 2 |  | 60%
| Task #C4 | 2018-01-26 | 26 | 2018-01-29 | 4 | 1.6 | 2.4 |  | 40%
| Task #C5 | 2018-01-22 | 22 | 2018-01-25 | 4 | 0.8 | 3.2 |  | 20%
Milestone D
| Task #D1 | 2018-01-15 | 15 | 2018-01-24 | 10 | 10 | 0 |  | 100%
| Task #D2 | 2018-01-25 | 25 | 2018-01-30 | 6 | 4.8 | 1.2 |  | 80%
| Task #D3 | 2018-01-24 | 24 | 2018-01-30 | 7 | 4.2 | 2.8 |  | 60%
| Task #D4 | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2 |  | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1